## Checklist
Project Plan - Checklist
Instructions: • Enter "Start Date" and "End Date" for each task. • Check off each task as it is completed. • Convert Checklist into Gantt Chart (if desired). • Ensure to provide regular status updates about project progress to relevant administrative and frontline stakeholders.
✓ | Start Date | End Date | Task
INITIATE (4 weeks)
Identify Program Lead/Champion
Establish criteria to select program champion. Consider both hard skills/experience as well as key soft skills, such as people and communication skills.
Assess staff members against criteria and determine preferred champion.
Determine preferred champion's willingness and capacity to take on the role/responsibility.
Communicate wound care initiative and Program Lead appointment across the organization.
Establish Interdisciplinary Working Group
Identify stakeholders within your organization that have: • Frontline clinical home health experience (i.e. workflows, protocols, policies) - CLINICAL • Insights into financial operations (i.e. staffing and supply costs) - FINANCIAL • Understanding of the current technology infrastructure - TECHNOLOGY Consider leveraging IHI's "Quality Improvement Team Member Matrix" to determine evaluate criteria and grade potential candidates. The Matrix will help ensure you have no gaps in your team. http://www.ihi.org/resources/Pages/Tools/Quality-Improvement-Team-Member-Matrix-Worksheet.aspx
Establish terms of reference (ToC) for the working group. The core sections of a ToC include: • Purpose • Objectives • Scope • Membership • Accountabilities • Budget • Meetings • Reporting Many examples can be easily found online. Typically, concision is best as it will allow the group to remain focused on their key objectives and responsibilities. An example of a good ToC template can be found here: https://en.healthnexus.ca/sites/en.healthnexus.ca/files/resources/torbuilder.pdf
Establish regular cadence for working group meetings (recommended, weekly).
Current State Assessment The current state assessment will inform multiple streams of project activity in the Develop and Implement Phases, including wound care experts, policies and protocols, technology and referral partnerships.
Complete an assessment of your current wound care population. Some questions to consider: • What is your current volume of wound patients? What percentage of your average daily census do they represent? • What types of wounds do you see? • What is your average episode length for wounds? • What is the average cost per wound episode? • What is the average number of visits per wound episode? • Where do your wound referrals originate (sources)?
Complete an assessment of your current wound policies and protocols. Some questions to consider: • What wound care policies and protocols do you have in place? • When were they last updated? • What evidence/best practice organizations have informed your policies? • How closely are your policies followed by your staff? • Do you know when and why staff deviate from policies? • Can you measure if your policies impact quality of care, patient outcomes or spending? • If utilizing wound care technology, is that included in your organizational policies (i.e. consent for photography)?
Complete an assessment of your current technology and tools. Some questions to consider: • Do you currently leverage any technology to provide wound care? • If so, how does this technology support or enhance your work? • What does the technology not do that would better support and enhance your work? • If not currently using any digital wound technology, what program goals would technology help you achieve? • What are the current gaps in your wound care delivery that technology could help solve?
DEVELOP (8 weeks)
Policies and Protocols
Understand your gaps in organizational wound care policies/protocols. Which policies are causing problems and/or are out of date (i.e. resulting in clinical practice variation, operational inefficiencies, etc.)?
Review wound care best practices from reputable wound care resources. Some of these sources have been identified in the Wound Care Expert Resources Guide.
Update wound care policies and protocols based on gaps analysis and review of best practices from reputable wound care resources.
Have updated policies reviewed and approved through your organization's P&P approval process and/or by the Program Lead.
Develop or provide access to training and educational resources for staff. These can include: • Free webinars • On-site skills training • Vendor training • Conference sessions • 1-on-1s
Technology
Conduct initial, internet research into digital wound management solution providers and the technology capabilities.
Review and revise the solution requirements (and their weighting) in the Technology Evaluation Rubric based on your agency's technology needs and initial research.
Contact 2-3 solution providers to request a solution demo.
Request a comprehensive proposal and quote from all solution providers. The proposal should provide details regarding the benefits of the technology, the approach for implementation and ongoing support, the pricing model, etc.)
Complete the "Technology Evaluation Rubric". This will help you determine the solution provider and technology best suited for your organization.
Complete negotiations and contract signing with your preferred solution provider.
Wound Care Expertise
If you don't currently have internal wound care expertise, create a profile for the wound care expertise you require. This profile should be based on the responsibilities you would need this role to fill and the experience that would be required to fulfill the responsibilities.
Determine if you have this expertise internally (and whether staff are fully competent or require greater education) or if you'll need to seek an external wound care expert (and if you require a full-time or part-time resource).
For an internal resource, determine what additional education, credentials or upskilling is needed (if any). This could include peer training, skills fairs, conference education sessions or professional certifications.
For an external resource, create a formal job description and posting to find and hire a wound expert.
Execute training / hiring plan for internal / external wound care expert(s).
Referral Partner Strategy
Based on current referral volumes, relationships and local discharge trends, create a prioritized list of institutional partners.
Determine what your potential institutional partners value in their home health partners (i.e. low readmission and hospitalization rates).
Develop marketing and sales material that appeals to the needs of institutional care providers and that demonstrates your wound care strengths and outcomes. In the Swift Medical webcast "Boost your Agency's Institutional Referrals", we explain effective methods to developing these materials to help distinguish your organization. This webcast is a part of the eBook followup package of tools and templates.
IMPLEMENT (12 weeks)
Policies and Protocols
Make your updated wound care policies and procedures easily accessible to staff at the point-of-care (i.e. deploy through digital wound management technology).
Deliver training and education sessions for relevant staff regarding new/updated policies and procedures.
Technology
Complete kick-off meeting with your technology provider.
Develop and approve project charter - agree on implementation plan, timelines and division of responsibilities with your technology partner.
Work with your technology partners to configure solution features and workflows for your organization.
Complete any technical integration work in collaboration with your technology provider.
Configure dashboards to monitor key business and clinical indicators and program success criteria.
Complete end-user training for all solution users. Technology partner can deliver training directly or can provide the materials and superuser training to support this task.
Go-live with digital wound management technology.
Referral Partner Strategy
Outreach: Connect with current and prospective referral partners to set up meetings (ideally, in-person meetings).
Meeting: Convey the benefits of partnering with your agency and the strengths of your wound care program. Use this time to better understand the needs and priorities of your partners to better position your value.
Followup: Continue to keep in regular communication with prospective partners to remain top of mind. Share marketing materials that demonstrate your proven clinical and patient outcomes.
Execution: Establish referral arrangements with institutional care providers.
Demonstrate Program Value
Determine the clinical, financial, operational and/or patient outcomes you will want to measure and assess to demonstrate the strength of your wound care program. Consider the metrics that will be valuable to your various stakeholder groups, such as referral partners and patients/their families.
Identify the data points and data sources required to measure each metric (i.e. some data can be found in CMS datasets, your EMR or other clinical and administrative systems).
Collect and record baseline data (timeframe before implementation of new wound care program and technology).
Establish evaluation timelines - at which intervals you will formally assess program success metrics.
OPTIMIZE (ongoing)
Ongoing Program Enhancement
Establish post-project working group meeting cadence (monthly or quarterly).
At this regularly scheduled working group meeting, you should: • Review and assess adherence to wound care policies and procedures • Establish education plan for new hires • Identify continuing staff education opportunities, based on gaps in performance or divergence from policies • Review program metrics and assess the progress of your wound care program (compared to baseline indicators) • Incorporate program success and benefits into your sales/marketing communications and materials (also consider for broader publication and promotion) • Collect and compile feedback about digital wound management solution to inform technology provider's product roadmap and feature backlog